## Dropdown (hidden)
Change Category | Yes or No
BAU | Y
Deployment/ Project | N
Restoration | NA
Infra/IT

## Summary
SR/ DR No.SCTASK3921718 PROJECT NAME: n/a
Document Version | Revision Date | Prepared By | Reviewed By | Testing Certification | Remarks/Document Changes Made
1 | <6/19/2024> | <Shweta Chopde> | <Prashant yergude> | Not applicable | <SCTASK4149524>
CHANGE SUMMARY
OBJECTIVE OF CHANGE | Configuration update for onecloud nginx prod servers ec2prdngnix01, ec2prdngnix02
CHANGE CATEGORY | Infra/IT
CHANGE SUMMARY | Configuration update for onecloud nginx prod servers ec2prdngnix01, ec2prdngnix02
DESCRIPTION | - What is the purpose of this activity? Configuration update for onecloud nginx prod servers ec2prdngnix01, ec2prdngnix02s - Why do we need this activity? update needed on onecloud nginx production servers configuration. - What are the changes? We received the configuration file from team just need to copy that configuration file in this location /etc/nginx/sites-available/infocast. Attaching file with this change. What triggered change? SCTASK4149524
AFFECTED SERVICES/SYSTEMS | <Specify the impacted or involved services/systems>
ACTIVITY IMPACT | <Specify the change impact, clearly indicate if the change will incur a downtime>
IMPACT DURATION | <Indicate the total duration of the downtime (in hh:mm format)>
ACTIVITY DURATION | <Indicate the total duration of the activity (in hh:mm format)>
TYPES OF DEPLOYMENT
CATEGORY | SUB-CATEGORY | IMPACTED SYSTEM
APPLICATION NAME | Code Fix/Configuration Fix/Code Change
Reference Change/PUR
User Access Management (UAMs)
Decomissioning Activity
Automation
DATA | Data Patch/Fix/Modification
Data Extraction
Data Migration (Copy/Transfer)
INFRASTRUCRTURE | Configuration Changes
Database Changes
Decomissioning Activity
| Hardware Upgrade/Refresh | Configuration update for onecloud nginx prod servers ec2prdngnix01, ec2prdngnix02
Patching Activity
Windows/Unix Server Deployment
TRANSFORMATION RELEASE
OTHERS | Indicate the other types of change
APPLICATION NAME | DURATION | START TIME |  | END TIME
n/a | n/a | n/a |  | n/a
TEST RESULTS AND ARTIFACTS
FUNCTIONAL TESTING |  | n/a
n/a
n/a
n/a
n/a
n/a
n/a
NON-FUNCTIONAL TESTING |  | n/a
n/a
n/a
n/a
OTHER INFRASTRUCTURE DETAILS
TARGET NODES | n/a
REQUIRED HARDWARE SPECS | n/a
REQUIRRED NMS INTEGRATION | n/a
REQUIRED SYS LOG INTEGRATION | n/a
REQUIRED ASSET RETIREMENT | n/a
OTHER INFORMATION (IF ANY) | n/a
PRR DETAILS
PRR SCORE %
IF PRR IS BELOW 100%, JUSTIFICATION IS REQUIRED | n/a
PRODUCTION OWNER APPROVAL (FROM MILIND) PROVIDED? NOTE: APPLICABLE IF PRR IS BELOW 100% | Y/N/NA | <Provide Production Owner Approval (Milind) if less than 100%> Y - Indicate the Document Center Number where evidence can be found (ex. email approval etc.) N - Indicate reason why approval has not yet been secured. N/A - Mark this section as N/A
OPERATIONAL REVIEWS
CAPACITY ASSESSMENT PERFORMED | Configuration update for onecloud nginx prod servers ec2prdngnix01, ec2prdngnix02
DATABASE REVIEW PERFORMED | n/a
STORAGE CAPACITY REVIEW PERFORMED | n/a
OTHERS | SCTASK4149524
Note on F3: Eduardo Jr Flores: This is to provide confirmation whether change was certified by Testing Team
Note on B15: Eduardo Jr Flores: Indicate the Type of Deployment by marking the applicable item/s with a "Y" below. Note: For Reference Change/PUR, Data Patch/Fix/Modification/Data Migration, please indicate the # of records.
Note on D17: Eduardo Jr Flores: Indicate impacted system
Note on D18: Eduardo Jr Flores: Provide Version Control (GitLab) Link
Note on D19: Eduardo Jr Flores: Indicate impacted system
Note on D20: Eduardo Jr Flores: Please indicate the # of records.
Note on D21: Eduardo Jr Flores: Indicate impacted system
Note on D22: Eduardo Jr Flores: Indicate impacted system
Note on D23: Eduardo Jr Flores: Indicate impacted system
Note on D24: Eduardo Jr Flores: Indicate impacted system
Note on D25: Eduardo Jr Flores: Please indicate the # of records.
Note on D26: Eduardo Jr Flores: Indicate impacted system
Note on D27: Eduardo Jr Flores: Indicate impacted system
Note on D28: Eduardo Jr Flores: Please indicate the # of records.
Note on D29: Eduardo Jr Flores: Indicate impacted system
Note on D30: Eduardo Jr Flores: Indicate impacted system
Note on D31: Eduardo Jr Flores: Indicate impacted system
Note on D32: Eduardo Jr Flores: Indicate impacted system
Note on D33: Eduardo Jr Flores: Indicate impacted system
Note on D34: Eduardo Jr Flores: Indicate impacted system
Note on D35: Eduardo Jr Flores: Indicate impacted system
Note on D36: Eduardo Jr Flores: Indicate impacted system
Note on D45: Eduardo Jr Flores: Indicate the Document Center Number were evidence can be found. Incase not applicable, please mark as N/A Dev. Team can provide this information
Note on D46: Eduardo Jr Flores: Indicate the Document Center Number were evidence can be found. Incase not applicable, please mark as N/A Dev. Team can provide this information
Note on D47: Eduardo Jr Flores: Indicate the Document Center Number were evidence can be found. Incase not applicable, please mark as N/A Dev. Team can provide this information
Note on D48: Eduardo Jr Flores: Indicate the Document Center Number were evidence can be found. Incase not applicable, please mark as N/A Dev. Team can provide this information
Note on D49: Eduardo Jr Flores: Indicate the Document Center Number were evidence can be found. Incase not applicable, please mark as N/A Dev. Team can provide this information
Note on D50: Eduardo Jr Flores: Indicate the Document Center Number were evidence can be found. Incase not applicable, please mark as N/A Dev. Team can provide this information
Note on D51: Eduardo Jr Flores: Indicate the Document Center Number were evidence can be found. Incase not applicable, please mark as N/A Dev. Team can provide this information
Note on D52: Eduardo Jr Flores: Indicate the Document Center Number were evidence can be found. Incase not applicable, please mark as N/A Dev. Team can provide this information
Note on D53: Eduardo Jr Flores: Indicate the Document Center Number were evidence can be found. Incase not applicable, please mark as N/A Dev. Team can provide this information
Note on F54: Eduardo Jr Flores: Indicate the Document Center Number were evidence can be found. Incase not applicable, please mark as N/A
Note on F55: Eduardo Jr Flores: Indicate the Document Center Number were evidence can be found. Incase not applicable, please mark as N/A
Note on D56: Eduardo Jr Flores: Indicate the Document Center Number. Incase not applicable, please provide a remark.
Note on B58: Eduardo Jr Flores: This is item should be filled out by Infra Team.
Note on B59: Eduardo Jr Flores: Eduardo Jr Flores: This is item should be filled out by Infra Team.
Note on B60: Eduardo Jr Flores: Eduardo Jr Flores: This is item should be filled out by Infra Team.
Note on B61: Eduardo Jr Flores: Eduardo Jr Flores: This is item should be filled out by Infra Team.
Note on B62: Eduardo Jr Flores: Eduardo Jr Flores: This is item should be filled out by Infra Team.
Note on B63: Eduardo Jr Flores: Eduardo Jr Flores: This is item should be filled out by Infra Team.
Note on C65: Eduardo Jr Flores: Indicate PRR Score Achieved 0-100%
Note on C66: Eduardo Jr Flores: Briefly explain why PRR is below 100%
Note on D67: Eduardo Jr Flores: No need to fill this out if PRR is 100%
Note on C70: Eduardo Jr Flores: Indicate the Document Center Number were evidence can be found. Incase not applicable, please justify why not applicable.
Note on C71: Eduardo Jr Flores: Indicate the Document Center Number were evidence can be found. Incase not applicable, please justify why not applicable.
Note on C72: Eduardo Jr Flores: Indicate the Document Center Number were evidence can be found. Incase not applicable, please justify why not applicable.

## sheet (hidden)
Summary
# | Requirement | Comment
1 | Change Objective
2 | ARF Data
3 | Service Affecting (y/n)
4 | Topology
5 | Pre Activities
6 | MOP
7 | Post Activities
8 | Rollback Plan
9 | Screenshot of Activities
10 | Implementor
11 | Tester
12 | Customer Tester (if required)
13 | Document History

## Procedure Overview (hidden)
[Implementation Steps]
|  | Responsible | Schedule | Service Impact
1 | Pre Activity Checklist |  | 10 Mins | none
2 | MoP Execution |  | 10 Mins | none
3 | Post AcitIvity Checklist |  | 10 Mins | none
4 | Back Out |  | 10 Mins | none

## Pre Activities (hidden)
Pre-Deployment Activities
Item # | Activity | Step | Implementor | Date | Start Time | End Time | Duration | Impact | Remarks | Artifacts
1 | [9 empty] | Insert supporting documents, files, records as reference for this particular step/procecedure
Note on B2: Eduardo Jr Flores: Indicate Config Backup Procedure Indicate saving of output in local computer Indicate Prechecks if necessary

## Deployment Activities
Pre-Deployment Activities
Item # | Activity | Step | Application Name | Implementor | Validator | Planned Time |  |  |  | Actual Time |  |  |  | Impact | Remarks | Artifacts
[6 empty] | Date | Start Time | End Time | Duration | Date | Start Time | End Time | Duration
1 | n/a | Take backup of nginx configuration file for infocast | Infocast | Fusion cloud Infra team | Fusion cloud Infra team | 18/06/2024 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Deployment Activities
Item # | Activity | Step | Application Name | Implementor | Validator | Planned Time |  |  |  | Actual Time |  |  |  | Impact | Remarks | Artifacts
[6 empty] | Date | Start Time | End Time | Duration | Date | Start Time | End Time | Duration
1 | Configuration update for onecloud nginx prod servers ec2prdngnix01, ec2prdngnix02 | Replace the nginx configuration file for infocast on location /etc/nginx/sites-available/infocast file attached with the change. | Infocast | Fusion cloud Infra team | Fusion cloud Infra team | 20/06/2024 | 22:00 | 0:00 | 2 Hrs
2 |  | Save the new configuration |  | Fusion cloud Infra team
3 |  | check nginx configuration with below command nginx -t |  | Fusion cloud Infra team
4 |  | After successful syntax varification reload nginx service |  | Fusion cloud Infra team
5 |  | Check with Ops and application for verfication if infocast URL is working as expected |  | Fusion cloud Infra team
Post Deployment Activities and Validation
Item # | Activity | Step | Application Name | Implementor | Validator | Planned Time |  |  |  | Actual Time |  |  |  | Impact | Remarks | Artifacts
[6 empty] | Date | Start Time | End Time | Duration | Date | Start Time | End Time | Duration
1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Note on C3: Eduardo Jr Flores: Application Team to fill out this section.
Note on D3: Eduardo Jr Flores: Application Team to fill out this section.
Note on E3: Eduardo Jr Flores: Application Team to fill this section.
Note on F3: Eduardo Jr Flores: Application and DM Team to fill out this section.
Note on G3: Eduardo Jr Flores: Application Team to fill out this section.
Note on P3: Eduardo Jr Flores: Application Team to fill out this section.
Note on Q3: Eduardo Jr Flores DM, Application Team, Implementer to fill out this section.
Note on R3: Eduardo Jr Flores: Application Team to fill out this section
Note on H4: Eduardo Jr Flores: DM Team to fill out this section.
Note on I4: Eduardo Jr Flores: Application Team to fill out this section.
Note on K4: Eduardo Jr Flores: Application Team to fill out this section. Value should be IN MINUTES ONLY
Note on L4: Eduardo Jr Flores: Implementer to fill out this section.
Note on M4: Eduardo Jr Flores: Implementer to fill out this section.
Note on O4: Eduardo Jr Flores: Implementer to fill out this section.
Note on C11: Eduardo Jr Flores: Application Team to fill out this section.
Note on D11: Eduardo Jr Flores: Application Team to fill out this section.
Note on E11: Eduardo Jr Flores: Application Team to fill this section.
Note on F11: Eduardo Jr Flores: Application and DM Team to fill out this section.
Note on G11: Eduardo Jr Flores: Application Team to fill out this section.
Note on P11: Eduardo Jr Flores: Application Team to fill out this section.
Note on Q11: Eduardo Jr Flores DM, Application Team, Implementer to fill out this section.
Note on R11: Eduardo Jr Flores: Application Team to fill out this section
Note on H12: Eduardo Jr Flores: DM Team to fill out this section.
Note on I12: Eduardo Jr Flores: Application Team to fill out this section.
Note on K12: Eduardo Jr Flores: Application Team to fill out this section.
Note on L12: Eduardo Jr Flores: Implementer to fill out this section.
Note on M12: Eduardo Jr Flores: Implementer to fill out this section.
Note on O12: Eduardo Jr Flores: Implementer to fill out this section.
Note on C19: Eduardo Jr Flores: Application Team to fill out this section.
Note on D19: Eduardo Jr Flores: Application Team to fill out this section.
Note on E19: Eduardo Jr Flores: Application Team to fill this section.
Note on F19: Eduardo Jr Flores: Application and DM Team to fill out this section.
Note on G19: Eduardo Jr Flores: Application Team to fill out this section.
Note on P19: Eduardo Jr Flores: Application Team to fill out this section.
Note on Q19: Eduardo Jr Flores DM, Application Team, Implementer to fill out this section.
Note on R19: Eduardo Jr Flores: Application Team to fill out this section
Note on H20: Eduardo Jr Flores: DM Team to fill out this section.
Note on I20: Eduardo Jr Flores: Application Team to fill out this section.
Note on K20: Eduardo Jr Flores: Application Team to fill out this section.
Note on L20: Eduardo Jr Flores: Implementer to fill out this section.
Note on M20: Eduardo Jr Flores: Implementer to fill out this section.
Note on O20: Eduardo Jr Flores: Implementer to fill out this section.

## Post Activities (hidden)
Post Deployment Activities and Validation
Item # | Activity | Step | Implementor | Date | Start Time | End Time | Duration | Impact | Remarks | Artifacts
1 | [9 empty] | Insert supporting documents, files, records as reference for this particular step/procecedure
If needed, add screenshots

## Rollback Plan
Rollback Plan
Item # | Activity | Step | Application Name | Implementor | Validator | Planned Time |  |  |  | Actual Time |  |  |  | Impact | Remarks | Artifacts
[6 empty] | Date | Start Time | End Time | Duration | Date | Start Time | End Time | Duration
1 | Roll Back Steps | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
2 | Restore the backed up configuration file
3 | Restart the nginx service
4 | Validate the Changes
Note on C3: Eduardo Jr Flores: Application Team to fill out this section.
Note on D3: Eduardo Jr Flores: Application Team to fill out this section.
Note on E3: Eduardo Jr Flores: Application Team to fill this section.
Note on F3: Eduardo Jr Flores: Application and DM Team to fill out this section.
Note on G3: Eduardo Jr Flores: Application Team to fill out this section.
Note on P3: Eduardo Jr Flores: Application Team to fill out this section.
Note on Q3: Eduardo Jr Flores DM, Application Team, Implementer to fill out this section.
Note on R3: Eduardo Jr Flores: Application Team to fill out this section
Note on H4: Eduardo Jr Flores: DM Team to fill out this section.
Note on I4: Eduardo Jr Flores: Application Team to fill out this section.
Note on K4: Eduardo Jr Flores: Application Team to fill out this section.
Note on L4: Eduardo Jr Flores: Implementer to fill out this section.
Note on M4: Eduardo Jr Flores: Implementer to fill out this section.
Note on O4: Eduardo Jr Flores: Implementer to fill out this section.

## Topology
From: [Provide system diagram of current state]
To: [Provide system diagram of future state]

## IT Ops Checklist
STANDARD OPERATIONS REQUIREMENT DETAILED CHECKLIST
DataCenter Operations (L1 Apps and L1 Infra)
|  | OPERATIONAL REQUIREMENTS | ADDITIONAL DESCRIPTION | NEW SYSTEM | UPDATE TO CORE MODULE OF THE SYSTEM | w/ PROJECTED INCREASE in VOLUME/TRAFFIC | ADDITIONAL APPLICATION MODULE/INSTANCE | REMARKS
24x7 OPERATIONAL DOCUMENTATION
1 | Operations Runguide detailing WHAT and HOW to…
|  | Routine Monitoring checklist > though SMART has standard checklist of system resources that need to be considered in routine system healthcheck, would like to still check with the provider if there are additional checking that SMART needs to consider to ensure system/service availability > checklist to include monitoring threshold to be defined in the system | Standard system resource monitored by SMART: > server resource - CPU, MEM, filesystem util > database resource (dB) - tablespace utilization, db locking, full tablescan, db alert log checking > application/system status checking, scheduled jobs, runtime frequency, pre-req (if any) > replicated db (DR dB) synchronization (should have checking on at least archive log sequence applied on DR) | MUST HAVE PRIOR PRODUCTION CUT-OVER | n/a | n/a | MUST HAVE PRIOR PRODUCTION CUT-OVER | INFRA RUN Guide to be cascaded by INFRA Team to INFRA Ops
|  | Alarms and Troubleshooting Guide > summary list of application alarms, its description and corresponding action/handling |  | MUST HAVE PRIOR PRODUCTION CUT-OVER | n/a | n/a | MUST HAVE PRIOR PRODUCTION CUT-OVER | To be condigured in APPSMAN
|  | Emergency Maintenance Guide > detailed steps on how to start applications/systems in case of unplanned system/server downtime taking into consideration pre-req tasks/other dependencies (if any), application lock file |  | MUST HAVE PRIOR PRODUCTION CUT-OVER | n/a | n/a | MUST HAVE PRIOR PRODUCTION CUT-OVER | Included in INFRA Turn-over
|  | Systems Operation Runguide to include detailed procedures on stopping/starting system modules taking into consideration 1. stop/start-up sequence 2. in-memory dB loading (if any) 3. systems application log checking 4. transactional logs tracing |  | MUST HAVE PRIOR PRODUCTION CUT-OVER | MUST HAVE PRIOR PRODUCTION CUT-OVER | n/a | MUST HAVE PRIOR PRODUCTION CUT-OVER | Included in Operation Manual
|  | Monitoring Tool Guide (in case there is a built-in monitoring tool included in the package/contract) > operational runguide on how to navigate the tool, interpret/handling of the alarms |  | MUST HAVE PRIOR PRODUCTION CUT-OVER | n/a | n/a | MUST HAVE PRIOR PRODUCTION CUT-OVER | Included in Operation Manual
|  | Data Replication/Mirroring, Housekeeping > SystemBack-up and Clean up > Data Backup and Clean-up > Database and applications synchronization/mirroring (if any) | to include OS and application (executables, config files, reference data backup) data online and data backup to tape retention (in agreement with Business proponent) to consider RTO/RPO in identifying the gap threshold | MUST HAVE PRIOR PRODUCTION CUT-OVER | n/a | n/a | MUST HAVE PRIOR PRODUCTION CUT-OVER | Included in INFRA Turn-over
2 | Reference Materials
|  | Functional Requirement Specification |  | MUST HAVE PRIOR PRODUCTION CUT-OVER | n/a | n/a | n/a | c/o DM/PM
|  | System Overview/Description/Architecture Guide |  | MUST HAVE PRIOR PRODUCTION CUT-OVER | MUST HAVE PRIOR PRODUCTION CUT-OVER | n/a | MUST HAVE PRIOR PRODUCTION CUT-OVER | Included in Operation Manual
- Network Diagram (detailed connectivity diagram)
- Service Topology
|  | - Detailed Transactions Flows (Voice, SMS, Data, etc) | to include details (scripts/executables, process logs, working directories, handling/archiving) of corresponding applications/modules running at backend to process those transactions.
- Application/system modules logs reference guide (how to interpret/translate those logs in terms of systems health checking)
- Reports Runguide (in case there exists built-in reports thay may be useful to Operations)
- Event Data Record Description or CDR Description
- IP Assignment and Port Description
|  | Hardware and Software Version and Release Notes |  | MUST HAVE PRIOR PRODUCTION CUT-OVER | n/a | n/a | n/a | Included in Operation Manual and INFRA turn-over
- Equipment Room Layout
- As-built Drawings
- Reference Manual
- Product Specification
- List of Software Version and Patch
- List of Software and Media License
- List of Technical Documents
- List of Spares
- Hardware Device SN Information List
- Software Media SN Information
- List of Future Upgrade
- Manual of Procedure
- Site Layout
|  | Capacity and Dimensioning |  | MUST HAVE PRIOR PRODUCTION CUT-OVER | MUST HAVE PRIOR PRODUCTION CUT-OVER | MUST HAVE PRIOR PRODUCTION CUT-OVER | MUST HAVE PRIOR PRODUCTION CUT-OVER | VT ongoing
- VT assessment
|  | Maintenance and Support Agreement |  | MUST HAVE PRIOR PRODUCTION CUT-OVER | n/a | n/a | n/a | For Scheduling : Dev and SI to cacade with OPS L1 and L2
|  | - babysitting/handholding agreement | to provision 24x7 onsite support at Vitro IDC on the entire babysitting/ handholding period (~3mos to ~6mos, refer to BabySitting/KT document)
|  | - technical support/maintenance agreement | TSA ( to include ticket handling/resolution and SLA)
- operations acceptance/turn-over
3 | TRAININGS/KT SESSIONS
|  | Formal |  | MUST HAVE PRIOR PRODUCTION CUT-OVER | n/a | n/a | MUST HAVE PRIOR PRODUCTION CUT-OVER | Included in Operation Manual and INFRA turn-over
|  | - Overview | 1. System/Technical Training covering the following points: * System or Product Platform Overview *End-to-End Network Topology * OS or DB Clustering as applicable * Provision for High Availability and High Scalability * Redundancy or Disaster Recovery Topology * Detailed Disaster Recovery Procedure 2. Functional Training covering the following points: * System/Module Functions * Business Requirements * Functional/Transactional Flow End-to-End 3. Operations and Maintenance Training covering the following points: *Hardware and Software Specs * Managing DB - DB Tables, Backup, Archive and Restore, Monitoring * Managing OS - Directory, Files, backup, Archive and Restore, Monitoring * Managing Applications - Input, Output, Logs
- Technical related
- Operations related
- System/Databse Administration related
Informal
- Technical Cascades
|  | - Hands-on/buddy system training (baby sitting period/knowledge transfer) | to cover application stop/start, logs tracing, transaction flow tracking
INTEGRATION TO EXISTING O&M tool(s)
|  | Monitoring Tool (Visual/Audible) - if any else we'll require them to be integrated with our existing tools |  | MUST HAVE PRIOR PRODUCTION CUT-OVER | MUST HAVE PRIOR PRODUCTION CUT-OVER | n/a | MUST HAVE PRIOR PRODUCTION CUT-OVER | Monitoring Tools via CACTI and AppsMan, for configuration of Void Codes
|  | - Performance Monitoring (Traffic) | Monitoring Tools: 1. Cacti - system and user failures; success rates; System performance (transactional throughput, graphical trends, tps) 2. Solarwinds - network elements 3. Apps Man - capacity thresholds (including e-mail alerts); Standard system resources 4. Oracle Enterprise Manager - Database monitoring 5. EMC Tools - Storage 6. UPM - Cronjobs, daemon processes 7. ION - Transactional monitoring (transaction state, VD, RC, Success, Failed (Business and Technical) 8. dEXTrnow - Ticketing
- System Monitoring
- Fault Monitoring
- Alarms Description
REPORTS
|  | Reports - if any, else logs where statistical/operational data can be obtained will be requested to be send to UDS |  | MUST HAVE PRIOR PRODUCTION CUT-OVER | MUST HAVE PRIOR PRODUCTION CUT-OVER | n/a | MUST HAVE PRIOR PRODUCTION CUT-OVER | Included in Operation Manual and INFRA turn-over
- Operational (application tps, tat)
- Statistical Report
- KPIs
TROUBLE / ESCALATION PROCESS
|  | Escalation Process, level of escalation and ticketing: |  | MUST HAVE PRIOR PRODUCTION CUT-OVER | MUST HAVE PRIOR PRODUCTION CUT-OVER | n/a | MUST HAVE PRIOR PRODUCTION CUT-OVER | Included in Operation Manual and INFRA turn-over
- Application/Software related
- Hardware related
- Ticketing System
SECURITY & AUDIT REQUIREMENTS
|  | PIA (Privacy Impact Analysis) c/o Business Proponent |  | MUST HAVE PRIOR PRODUCTION CUT-OVER | n/a | n/a | n/a | c/o DM/PM
|  | Resiliency/DRP | If no DR, a signed Risk Acceptance from the Info Asset Owner (Business Proponent) shld be submitted to Dcops Infra | MUST HAVE PRIOR PRODUCTION CUT-OVER | MUST HAVE PRIOR PRODUCTION CUT-OVER | n/a | MUST HAVE PRIOR PRODUCTION CUT-OVER | Included in Operation Manual and INFRA turn-over
- High Level Diagram with Locations
|  | - Disaster Recovery Solution and Comprehensive DR User Manual | User manual should be available as reference of the Operator on duty to readily execute the procedure considering all elements needed to recover the service
|  | - DR documentation | S1 to S7 DRP documentation
|  | APM – UAM : Info asset owner / custodian | with identified Info Asset Owner/Custodian | MUST HAVE PRIOR PRODUCTION CUT-OVER | n/a | n/a | MUST HAVE PRIOR PRODUCTION CUT-OVER | c/o DM/PM
Turnover Checklist | Docs / Info / Artifacts | Responsible | Remarks
1. Project | Project Summary/Description | Dev team
| System Diagram with Transaction Flow | Dev team
| Topology with Location and IP Address info | Dev team/Sysad
| Software and Hardware inventory | Sysad
| HA and DR Design | DBA,SYSAD
| Backup and Recovery | DBA,SYSAD
| System Owners and Production/Dev Support | Dev team
2. Database | DB Version | DBA
| Metadata Documentation with Object Description | Dev Team
| Interfacing DB and Data Sharing inventory | Dev Team
| Maintenance | DBA
| Log Management (eg: Oracle=Archive Log, SQL=Trans Log) | DBA
| DB Object auto management (eg: Partitioning, etc) | DBA
| Auto Jobs inventory | DBA
| Capacity with Growth projection | Dev Team
| Data retention with Archiving and Purging Policy | DBA
| Backup Policy (Metadata, Full/Incremental) & enrollment | DBA
| MIA enrollment | SYSAD,DBA
| User Accounts Listing | SYSAD,DBA
| HA/DR Solution | SYSAD,DBA
| Master List DB Inventory update | DBA
Turnover Checklist | Docs / Info / Artifacts | Responsible | Remarks
3. Server | Server Info | SYSAD
| Hostname, IP | SYSAD
| Specs (Mem and CPU) | SYSAD
| Location, ILO, etc… | SYSAD
| Config settings inventory | SYSAD
| Storage inventory with specs | SYSAD
| Backup Policy & enrollment | SYSAD
| Master List Server Inventory update | SYSAD
| Vulnerability Assessment compliance from CSOG | SYSAD
| Supplier/Vendor Support | SYSAD
4. Network | Loadbalancer | SYSAD
| Ports open per server | SYSAD
5. Infra/Ops compliance | Ops requirement compliance | Representative from all
| CCF and DRF for new Server/DB/Apps provisioning | Requestor

## Contact List
ROLE | FULL NAME | AREA | E-MAIL | MOBILE NO.
Fusion cloud Infra team | Devi prasad goddi/Anjul Singh | AIA | devivaraprasad.goddi@amdocs.com,anjul.singh@amdocs.com | 7416481909/7275177775
| John Samonte |  | JohnRoderick.Samonte@amdocs.com | +639209519383

## ARF Data (hidden)
ARF (AMDOCS Request Form) is applicable to Infrastructure Teams only
|  |  | AMDOCS Access Request Form | [8 empty] | Control No.____
Reminders: 1. Implementation is on maintenance window only. Lead time: 4 working days 2. Approval of the Source and Destination System Owner is required. 3. If possible, provied a network diagram.
Request Info
|  | Requestor's Name |  | :Bai Laila Abdullah |  |  |  | Date of Request |  | : July 12, 2019
|  | Dept. / Group |  | :SI-VAS |  |  |  | Date Needed |  | : July 15, 2019
|  | Contact Number |  | :09178490208 |  |  |  | Project Name (if any) |  | :AEP
|  | Company |  | :SMART |  |  |  | Reason for Request |  | : Firewall connection from AEP to CDP
|  | Manager |  | :Earl Aranza
|  | Equipment/s |  | Type | Services |  |  | Globa IP |  |  | Yes | No
|  |  |  | Frontend |  |  |  | Do you require a dedicated Global/Public IP
|  |  |  | Backend |  |  |  | Global/Public IP Requests must be approved by TSM
| Item No. | Source Information |  |  |  |  | Destination Information |  |  |  | Expected No of Session | Expected Bandwidth usage | Duration
|  | IP Address |  | Protocol & Port No. | Location | System Owner Approval (Name with Signature) | IP Address | Protocol & Port No. | Location | System Owner Approval (Name with Signature)
| 1 | 10.109.46.100 |  | Any |  |  | 10.109.177.175 | HTTP 19311 19312 19313 19315 19316 |  |  | N/A
| 2 | 10.109.46.101 |  | Any |  |  | 10.109.177.175 |  |  |  | N/A
| 3 | 10.109.46.102 |  | Any |  |  | 10.109.177.175 |  |  |  | N/A
4
5
NETWORK ADMINISTRATOR SECTION
|  | Business Impact: o Service Affecting o Non-Service Affecting | [5 empty] | Endorsed by:
[8 empty] | SMART |  | :
[8 empty] | PLDT |  | :
[8 empty] | DIGITEL |  | :
[8 empty] | Amdocs |  | :
|  | Remarks : Current NAT IP used is 10.111.40.85 | [5 empty] | Implemented by:
[8 empty] | Amdocs |  | :